## Slide 1: St. Luke’s RC Primary School School Improvement Plan 2016.2017
ASG
Visible Learning
* Shared language of learning
across the school
Growth mindset evident
across the school
Formative assessment
strategies in place across the school
* Consistent understanding and
use of learning intentions and success criteria
Health and Wellbeing
Pupil nurture/emotional
wellbeing group introduced
HWB frameworks for all pupils
Pupil chronologies in place
for all pupils
School vision, values and aims reviewed in school
After school clubs evident in school
Ongoing
Outdoor learning across the school
Residential in place for two stages of school
French learning in all classes
MUMP used for planning and teaching of maths in all classes
Pupil Focus Group review
Data analysis to inform next steps
RE programme in place in all classes
Reading
Consistent approaches to teaching reading across the school
Consistency in planning and assessing reading
Pupil involvement in assessing progress and next steps
Whole school approach to reading for enjoyment
Community
Programme of planned events
for campus partners
Learning links established across stages of each school
Transition music initiative in
place in both schools

## Slide 2
Reading
Consistent approaches to teaching reading across the school
Consistency in planning and assessing reading
Pupil involvement in assessing progress and next steps
Whole school approach to reading for enjoyment
What will we do?
Skills based approach to all reading across the school
Reciprocal reading approaches introduced in P4-P7
Reading aloud approaches developed in all classes
Thinking reader approach used in group reading sessions for P3-P7
Reading for enjoyment a whole school focus with key events planned across the year
Paired reading to be led by P6/7 pupils for P1/2 pupils
Vocabulary enrichment a key focus for all classes across the school
In planning, experiences and outcomes will be linked to significant aspects of learning
Pupil matrix will be created for each level linked to significant aspects of learning
Assessments will be linked to significant aspects of learning, and for achieving a level
When will we do it?
Planning to start in August following session at In-set day
All pupils to attend Edinburgh Book Festival in August to make reading real
‘What is Reading?’ whole school introduction in August 2016
CAT session in September on skills approach to reading
Skills approach evident in weekly planning from October
Whole school reading for enjoyment initiative linked with campus school and local community, October to December
Thinking reader approach to be introduced in all classes from October 2016
Reciprocal reading skills developed in classes January 2017
Reciprocal reading approach in place from February 2017
Vocabulary enrichment session for all staff Aug-Oct. Midlothian framework to be used in all classes from October 2016 on weekly basis
Staff development group to create pupil matrix between August and November. To be used by pupils from January 2017
Staff development team to devise and trial class based activities linking assessment to significant aspects of learning by December 2016. Trialling January to Easter 2017.
How will we monitor it?
SMT to monitor weekly planning on server from August 2016. Feedback to staff in mid September and any adaptations made. Conitnues in assessment calendar across session
SMT to monitor block planning to check for key elements of reading are planned for across the school
Walk throughs by SMT, staff and pupils to look for key elements of new reading practice. Planned in assessment calendar
Pupil focus groups to be taken once per term (in monitoring calendar) to discuss changes and approaches to reading in class
Pupils to discuss individual reading matrix with SMT at Easter and Summer to monitor useage and understanding by pupils
SMT/working group to liaise with campus school and local community to ensure reading challenge is a success and understood by all

## Slide 3
What will we do?
Language of learning devised from research and relevant to our school
Language of learning words shared weekly through assemblies and vertical learning groups
Language of learning interactive display in all classes and referred to across the whole school day
Intelligence and the brain explored by all pupils and linked to growth mindset
Staff change use of vocabulary to link with growth mindset
Awards systems in school to be changed to link with growth mindset
Use of learning intentions and success criteria reviewed for all staff
Learning intentions and success criteria used in all classes for all lessons and reviewed regularly
Pupil awareness of relevance of learning intentions and success criteria to be raised
Pupils to use learning intentions and success criteria to discuss their learning
When will we do it?
By August staff will have reviewed current approaches to award systems in school and altered in line with growth mindset
By August staff will be aware of impact of vocabulary in class, and will use alternative words linked to grouping etc
By October all pupils will have been introduced to each of the learning words and characters will have been created for each word
By December, each class will have an interactive display and pupils will refer to this when asked to discuss their learning within the classroom
By October, working group will have devised a programme for all pupils being introduced to the brain and its workings
By December all pupils will have completed a programme of learning linked to growth mindset and the brain
By September, staff will have reviewed the purpose of learning intentions and success criteria and how this will be shared throughout learning
By October, all staff will be sharing learning intentions and success criteria routinely and in a consistent way throughout the school and all pupils will be able to identify these
By December, all pupils will be able to refer to their progress in relation to the learning intentions and success criteria during a lesson
By February, teachers will regularly be referring to the language of learning and learning intentions and success criteria throughout the school day.
By February pupils will be able to describe what they are learning and how they are learning it, linking to language of learning and success criteria
How will we monitor it?
Learning intentions and success criteria to be evident on weekly planning for all areas. SMT to monitor as part of weekly planning. Staff meetings for whole school analysis of consistency and next steps – two per term until Christmas and then review
Language of learning will be evidenced in all classrooms through interactive displays. Observations will have a focus on use of learning intention and success criteria as well as language of learning before Christmas (see monitoring and assessment calendar)
Walk throughs by SMT, colleagues and pupils, as outlined in monitoring and assessment calendar
Focus groups of pupils (term 3 and 4) linked to learning intentions and success criteria and reading matrix
Detailed information from school working group
Visible Learning
* Shared language of learning
across the school
Growth mindset evident
across the school
Formative assessment
strategies in place across the school
* Consistent understanding and
use of learning intentions and success criteria
Concentrate
Perseverance
Cooperate
Explorer
Resourceful
Reflective
Imaginative
Resilient

## Slide 4
What will we do?
SMT to discuss nurture and emotional wellbeing group with behaviour support teacher
SMT to visit Lawfield Primary School to observe practice within an established group
Pupils to be identified by class teachers
SMT to introduce a small nurture group to meet daily within school to support specific pupils
HWB frameworks in place for all pupils, outlining supports and agencies in place
Chronologies created for each pupil for staff to record information
School vision, values and aims to be reviewed in school by staff team
All staff to support pupils by offering after school opportunities for pupils across the year
When will we do it?
By August, SMT will have discussed nurture group with behaviour support teacher
By September SMT will have visited local school to observe and discuss nurture groups
By September pupils will be identified for support as part of a nurture group
By September a safe place will be established in school for pupils to go to in times of crisis
By August initial frameworks will have been set up by HT
All staff to be familiar with frameworks by end of August
Chronologies to be in place for August for use by all staff who come in to contact with families
School vision, values and aims to be reviewed at CAT session by September 2016 with School Group Manager to lead
Staff to agree a calendar of after school clubs by September 2016
How will we monitor it?
SMT to introduce and lead nurture activities together in school
Staff to feedback to SMT at fortnightly staff meetings on impact and next steps established (standing agenda item on staff meeting)
Chronologies to be reviewed in October 2016 re effectiveness and any adaptations made
SMT and SfL teacher to meet monthly to review HWB frameworks and update accordingly
Calendar of after school clubs created in September. PT to monitor and to advise staff when clubs are due to start etc
Health and Wellbeing
Pupil nurture/emotional
wellbeing group introduced
HWB frameworks for all pupils
Pupil chronologies in place
for all pupils
School vision, values and aims reviewed in school
After school clubs evident in school

## Slide 5
What will we do?
Whole school to meet with Mayfield Primary School to review work from term 4 and plan shared events and learning opportunities
SMTs and working groups from each school to meet to prioritise events and create shared calendar of events
Music initiative established in nursery planned to continue with P1 pupils from both school
When will we do it?
August in-service will provide opportunities for shared planning to take place
By September a shared calendar of events will be created for the two school
Music initiative will take place in August 2016 for both schools
How will we monitor it?
SMT to ensure that calendar of events is created and adhered to
Regular SMT meetings between the two schools to ensure events are planned in advance and all information is clear for both schools
Small scale working group to meet to ensure staff views are represented in planning opportunities
Community
Programme of planned events
for campus partners
Learning links established across stages of each school
Transition music initiative in
place in both schools

## Slide 6
What will we do?
Outdoor learning opportunities to be planned for in all classes using school grounds and external spaces where appropriate
Outdoor learning experiences to be offered to all classes, linked to outdoor awards wherever possible
Two residential experiences to be offered in school
All classes to have French as part of weekly learning in class
All classes to have French as part of everyday vocabulary and instructions within class
MUMP to be used in all classes as planning tool for maths
Pupil focus groups to be in place across the school, with areas of learning reviewed
Clear framework for focus groups to be established across the school
Pupil focus groups to report back in assemblies following sessions
Staff to continue to analyse data in school to identify class and school trends, inform next steps and improve consistency through valuing expertise and skill set of staff members
God’s Loving Plan to be used in all classes and planned for across the school year, linked to health and wellbeing wherever possible
When will we do it?
Outdoor learning to be evident in weekly planning from August 2016
Residential experiences in place for February and March 2017
French learning to be evident in weekly planning from August 2016
MUMP to be evident in weekly and block planning from August 2016
Framework for pupil focus groups to be established at August inservice
Data analysis to be planned for in staff meetings across the year (monthly agenda item)
RE planning to be evident in weekly and block planning from August
How will we monitor it?
Weekly planning to be monitored by SMT from September 2016
Weekly planning to be monitored at staff meetings from September 2016 (monthly) to ensure consistency
Pupil focus groups require to report back at each assembly following sessions to ensure progress is shared with whole school community
Data to be reviewed at key times in line with assessment and monitoring calendar for formal assessments and monthly as part of staff meetings7
Review of impact of outdoor residential with parents of pupils who have attended over past two sessions (P4 pupils) to ensure success for next year’s planning
Review new centre for P7 pupils by staff attending in comparison to previous centre and ASG linked residential before decisions are made for 2017.2018
Ongoing
Outdoor learning across the school
Residential in place for two stages of school
French learning in all classes
MUMP used for planning and teaching of maths in all classes
Pupil Focus Group review
Data analysis to inform next steps
RE programme in place in all classes

## Slide 7
What will we do?
When will we do it?
How will we monitor it?
ASG